## US Launch Plan
Planner Plan: Pashun Pro Tee - US Launch
Create this plan in Planner, add the buckets below, then add each task with its assignee and due date.
Bucket | Task title | Assigned to | Due date | Progress | Notes
Sourcing | Confirm Ridgeline Apparel Supply fabric order for US range | Jamie Jordan | 2026-01-23 | Completed | Performance blend, Navy & Charcoal, $4.10/metre, 2,000 units
Sourcing | Track fabric delivery against 3-week lead time | Jamie Jordan | 2026-02-04 | In progress | Blocks production start
Production | Schedule cut & sew run for 2,500-unit order | Jamie Jordan | 2026-02-11 | Not started | Depends on fabric delivery
Finance | Raise invoice PSP-INV-1042 for first US wholesale order | Morgan Reyes | 2026-02-05 | Completed | 2,500 units, $22,500 total
Finance | Reconcile Q1 actuals against US Forecast tab | Morgan Reyes | 2026-02-20 | Not started | Ahead of Monthly US Sales Review
Marketing | Finalise Pashun_Pro_Tee_Pitch.pptx for internal briefing | Paul Ashun | 2026-01-30 | Completed
Launch | Set up US Launch Checklist in OneNote | Paul Ashun | 2026-01-20 | Completed